## Sheet1 (hidden)
2025 Capstone Project Schedule and Plan
Initial Plan for Milstones
Stage | Weeks | External Milestone | Internal Milestone | Deliverables | Soft Deadline | In-Course Deadline
Stage 0 | 1 | Kickoff Meeting | Define Project Objectives and Scope
| 2 | Milestone 1 |  | Establish Project Timeline | 2025-01-14 | 2025-01-20
|  | Milestone 2 | Complete Market Research | Assign Team Member Responsibilities | 2025-01-14 | 2025-01-27
Stage 1 | 3 |  | Collect a drone and an arm | BOM, Parts and Assembly Drawings | 2025-01-20
| 4 |  | Integrate Robotic Arm with UAV | Photos | 2025-01-30
| 5 |  | Conduct Testing of Prototype Robotic Arm | Demo1 Photos and Video | 2025-02-10
| 6 | Milestone 2 |  | Interim Report | 2025-02-13 | 2025-02-14
Stage 2 | 7 |  | Start Advance Testing | BOM, Parts and Assembly Drawings | 2025-02-17
| 9 |  | Conduct Testing of Final Robotic Arm | Photos | 2025-03-06
| 9 | Milestone 3 |  | Preliminary Design Drawings/Flowcharts | 2025-03-06 | 2025-03-07
Stage 3 | 10 |  | Conduct Integrated Field Testing of UAV and Robotic Arm | Demo2 Photos and Video | 2025-03-10
| 12 |  | Initiate Writing Report | First Draft | 2025-03-24
Buffer Time for Flexible Plan
| 13 | Milestone 4 |  | Final Engineering Report | 2025-04-03 | 2025-04-04
|  | Milestone 5 |  | Conference Paper | 2025-04-03 | 2025-04-04
GANTT CHART | [13 empty] | A Gantt chart's visual timeline allows you to see details about each task as well as project dependencies.
PROJECT TITLE |  | Development of a Robotic Arm for UAV Integration |  |  |  |  | Team Member: Jeongyun Jeong, Jerin Johnson, Thivyan Suthenthiran, Aksh Sharma
WBS NUMBER | TASK TITLE |  |  | TASK OWNER |  | START DATE | DUE DATE | DURATION | Deliverables | PCT OF TASK COMPLETE | PHASE ZERO | [10 empty] | PHASE ONE | [27 empty] | PHASE TWO | [20 empty] | PHASE THREE |  |  | PHASE FOUR
[11 empty] | WEEK 1 | [6 empty] | WEEK 2 | [6 empty] | WEEK 3 | [6 empty] | WEEK 4 | [6 empty] | WEEK 5 | [6 empty] | WEEK 6 | [6 empty] | WEEK 7 | [6 empty] | WEEK 8 | [6 empty] | WEEK 9 | [6 empty] | WEEK 10 | [6 empty] | WEEK 11 | [6 empty] | WEEK 12 | [6 empty] | WEEK 13 | [6 empty] | WEEK 14 | [6 empty] | WEEK 15 | [6 empty] | WEEK 16
[11 empty] | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S
[8 empty] | Days |  |  | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27
0 | Project Conception and Initiation
0.1 | Project Plan |  |  | All |  | 2025-01-16 | 2025-01-28 | 12 |  | 100%
0.1.1 | Project Timeline |  |  | All |  | 2025-01-16 | 2025-01-20 | 4 | Timeline | 100% | bar: WEEK 2 R 16 to WEEK 3 M 20
0.1.2 | Resposibility Assignment |  |  | All |  | 2025-01-16 | 2025-01-27 | 11 | Team Member Resposibilities | 100% | bar: WEEK 2 R 16 to WEEK 4 M 27
0.1.3 | LIT Review |  |  | All |  | 2025-01-17 | 2025-01-20 | 3 |  | 100% | bar: WEEK 2 F 17 to WEEK 3 M 20
1 | Mechanical Design
1.1 | Robotic Arm Design |  |  | Jerin |  | 2025-01-16 | 2025-01-23 | 7 |  | 0%
1.1.1 | Literature review |  |  | Jerin |  | 2025-01-18 | 2025-01-21 | 3 | Review Arm Architechtures and Designs | 5% | bar: WEEK 2 S 18 to WEEK 3 T 21
1.1.2 | Collect 3D model of Drone |  |  | Jerin |  | 2025-01-16 | 2025-01-16 | 0 |  | 100% | bar: WEEK 2 R 16
1.1.3 | Calculation |  |  | Jeongyun |  | 2025-01-18 | 2025-01-19 | 1 |  | 100% | bar: WEEK 2 S 18 to WEEK 2 S 19
1.1.4 | Make a model for Drone-Arm Interface |  |  | Jerin, Jeongyun |  | 2025-01-20 | 2025-01-27 | 7 |  | 100% | bar: WEEK 3 M 20 to WEEK 4 M 27
1.1.5 | Make a Model for Arm |  |  | Jerin, Jeongyun |  | 2025-01-20 | 2025-01-23 | 3 |  | 80% | bar: WEEK 3 M 20 to WEEK 3 R 23
1.1.6 | Make a Model for Gripper |  |  | Jeongyun |  | 2025-01-16 | 2025-01-23 | 7 |  | 100% | bar: WEEK 2 R 16 to WEEK 3 R 23
1.1.7 | FEA of Arm |  |  | Jerin |  | 2025-01-23 | 2025-01-25 | 2 |  | 0% | bar: WEEK 3 R 23 to WEEK 3 S 25
1.1.8 | FEA of Gripper |  |  | Jerin |  | 2025-01-25 | 2025-01-26 | 1 |  | 0% | bar: WEEK 3 S 25 to WEEK 3 S 26
1.1.9 | Get BOM and Order |  |  | All |  | 2025-01-16 | 2025-01-24 | 8 |  | 90% | bar: WEEK 2 R 16 to WEEK 3 R 23
1.2 | Manufacturing |  |  |  |  | 2025-01-19 | 2025-01-24 | 5 |  | 0%
1.2.1 | 3D Printing |  |  | Jeongyun |  | 2025-01-22 | 2025-01-24 | 2 |  | 40% | bar: WEEK 2 S 19 to WEEK 3 T 21
1.2.2 | Assembly |  |  | All, Jeongyun |  | 2025-01-23 | 2025-01-24 | 1 |  | 0% | bar: WEEK 3 W 22 to WEEK 3 F 24
1.3 | Electronic & Computer Design |  |  |  |  | 2025-01-16 | 2025-02-08 | 22 |  | 0%
1.3.1 | Research and select suitable electronics |  |  | Aksh |  | 2025-01-16 | 2025-01-20 | 4 |  | 0% | bar: WEEK 2 R 16 to WEEK 3 M 20
1.3.2 | Test Control System (servo, sensors only) |  |  | Aksh |  | 2025-01-20 | 2025-01-25 | 5 |  | 0% | bar: WEEK 3 M 20 to WEEK 3 S 26
1.3.3 | Design electrical circuits for the robotics arm |  |  | Aksh |  | 2025-01-23 | 2025-01-28 | 5 |  | 0% | bar: WEEK 3 R 23 to WEEK 4 T 28
1.3.4 | Create control system architecture (including feedback loop, sensor integration and user interface) |  |  | Aksh |  | 2025-01-25 | 2025-01-28 | 3 |  | 0% | bar: WEEK 3 F 24 to WEEK 4 M 27
1.3.5 | Implement sensors on the arm |  |  | Aksh |  | 2025-01-24 | 2025-02-01 | 7 |  | 0% | bar: WEEK 3 S 25 to WEEK 4 W 29
1.3.6 | Assemble/Test Control System attaching on arm |  |  | Aksh |  | 2025-02-01 | 2025-02-05 | 4 |  | 0% | bar: WEEK 4 S 1 to WEEK 5 W 5
1.3.7 | Implement safety mechanisms (emergency stops, overload protection) |  |  | Aksh |  | 2025-01-24 | 2025-02-01 | 7 |  | 0% | bar: WEEK 3 F 24 to WEEK 4 S 1
1.3.8 | Calibrate sensors and fine-tune control algorithm for optimal performance |  |  | Aksh |  | 2025-02-05 | 2025-02-08 | 3 |  | 0% | bar: WEEK 5 W 5 to WEEK 5 S 8
1.4 | Assemble of UAV & Arm Subsystems |  |  | All |  | 2025-01-27 | 2025-02-09 | 12 |  | 0%
1.4.1 | Get Drone model |  |  | Jeongyun |  | 2025-01-27 | 2025-01-27 | 0 |  | 0% | bar: WEEK 4 M 27
1.4.2 | Implement Arm with UAV |  |  | All |  | 2025-01-28 | 2025-02-05 | 7 |  | 0% | bar: WEEK 4 T 28 to WEEK 5 S 9
1.5 | Demo working model with Dr. Sharifi |  |  | All |  | 2025-02-10 | 2025-02-10 | 0 | Working Arm | 0% | bar: WEEK 6 M 10
1.6 | Write Interim Report |  |  | All, Thivyan |  | 2025-02-06 | 2025-02-14 | 8 | Interim Report | 0% | bar: WEEK 5 R 6 to WEEK 6 R 13
2 | Advance Design
2.1 | Test Benchmark |  |  | All |  | 2025-02-10 | 2025-02-15 | 5 |  | 0% | bar: WEEK 6 M 10 to WEEK 6 R 13
2.2 | Add advanced part and program |  |  | All |  | 2025-02-13 | 2025-02-27 | 14 |  | 0%
2.2.1 | 3D modeling/printing advanced part |  |  | Jerin, Jeongyun |  | 2025-02-13 | 2025-02-19 | 6 |  | 0% | bar: WEEK 6 R 13 to WEEK 6 S 16
2.2.2 | Program advanced control system |  |  | Aksh |  | 2025-02-13 | 2025-02-20 | 7 |  | 0% | bar: WEEK 6 R 13 to WEEK 7 R 20
2.2.3 | Finish up Advanced model |  |  | All |  | 2025-02-20 | 2025-02-27 | 7 |  | 0% | bar: WEEK 7 R 20 to WEEK 8 R 27
2.3 | Test Final Advanced model |  |  | All |  | 2025-02-27 | 2025-02-28 | 1 | Working Advanced Model | 0% | bar: WEEK 8 R 27 to WEEK 8 F 28
2.4 | Preliminary Design Drawings/Flowcharts |  |  | All |  | 2025-03-01 | 2025-03-06 | 5 | Preliminary Design Drawings/Flowcharts | 0% | bar: WEEK 8 S 1 to WEEK 9 R 6
3 | Final Field Test
3.1 | Conduct Integrated Field Testing of UAV and Robotic Arm |  |  | All |  | 2025-03-07 | 2025-03-09 | 2 |  | 0% | bar: WEEK 9 F 7 to WEEK 9 S 9
3.2 | Demo Final Working Model with Dr. Sharifi |  |  | All |  | 2025-03-10 | 2025-03-10 | 0 |  | 0% | bar: WEEK 9 F 7 to WEEK 9 S 9
4 | Project Report and Presentation
4.1 | Report |  |  | All, Thivyan |  | 2025-03-10 | 2025-04-03 | 23 | Report | 0%
4.1.1 | Abstract |  |  | Thivyan |  | 2025-03-10 | 2025-03-11 | 1 |  | 0% | bar: WEEK 10 M 10 to WEEK 10 T 11
4.1.2 | Project Definition |  |  | Thivyan |  | 2025-03-11 | 2025-03-12 | 1 |  | 0% | bar: WEEK 10 T 11 to WEEK 10 W 12
4.1.3 | Introduction |  |  | Thivyan |  | 2025-03-12 | 2025-03-13 | 1 |  | 0% | bar: WEEK 10 W 12 to WEEK 10 R 13
4.1.4 | Theory |  |  | Jeongyun |  | 2025-03-10 | 2025-03-13 | 3 |  | 0% | bar: WEEK 10 M 10 to WEEK 10 R 13
4.1.5 | Morphological Chart |  |  | Thivyan |  | 2025-03-13 | 2025-03-13 | 0 |  | 0% | bar: WEEK 10 R 13
4.1.6 | Mathematical Modelling / Calculation |  |  | Jeongyun |  | 2025-03-13 | 2025-03-14 | 1 |  | 0% | bar: WEEK 10 R 13 to WEEK 10 F 14
4.1.7 | Failure Mode and Effect Analysis |  |  | Thivyan |  | 2025-03-13 | 2025-03-15 | 2 |  | 0% | bar: WEEK 10 R 13 to WEEK 10 S 15
4.1.8 | Model-Based Systems Engineering (MBSE) |  |  | Thivyan |  | 2025-03-15 | 2025-03-18 | 3 |  | 0% | bar: WEEK 10 S 15 to WEEK 11 T 18
4.1.9 | Electrical Schematic Diagram |  |  | Jeongyun |  | 2025-03-14 | 2025-03-14 | 0 |  | 0% | bar: WEEK 10 F 14
4.1.10 | Data Analysis and Interpretations |  |  | Jeongyun |  | 2025-03-14 | 2025-03-19 | 5 |  | 0% | bar: WEEK 10 F 14 to WEEK 11 W 19
4.1.11 | Conclusions and Findings |  |  | Thivyan, All |  | 2025-03-19 | 2025-03-20 | 1 |  | 0% | bar: WEEK 11 W 19 to WEEK 11 R 20
4.1.12 | Suggestions and Recommendations |  |  | Thivyan |  | 2025-03-21 | 2025-03-22 | 1 |  | 0% | bar: WEEK 11 F 21 to WEEK 11 S 22
4.1.13 | BOM |  |  | Jeongyun, Jerin |  | 2025-03-22 | 2025-03-23 | 1 |  | 0% | bar: WEEK 11 S 22 to WEEK 11 S 23
4.1.14 | References |  |  | Thivyan |  | 2025-03-24 | 2025-03-25 | 1 |  | 0% | bar: WEEK 12 M 24 to WEEK 12 T 25
4.1.15 | 3D Drawings |  |  | Jeongyun, Jerin |  | 2025-03-25 | 2025-03-26 | 1 |  | 0% | bar: WEEK 12 T 25 to WEEK 12 W 26
4.1.16 | Formatting & Revise |  |  | All, Thivyan |  | 2025-03-25 | 2025-04-03 | 8 | Engineering Report | 0% | bar: WEEK 12 T 25 to WEEK 13 R 3
4.2 | Conference Paper |  |  | Thivyan, All |  | 2025-03-10 | 2025-03-21 | 11 | Conference Paper | 0% | bar: WEEK 10 M 10 to WEEK 11 F 21
4.3 | Presentation |  |  | All |  | 2025-04-05 | 2025-04-25 | 20 | Presentation | 0%
4.3.1 | Poster |  |  | All |  | 2025-04-05 | 2025-04-17 | 12 |  | 0% | bar: WEEK 13 F 4 to WEEK 15 R 17

## RACI MATRIX (hidden)
Task | Jerin | Jeongyun | Aksh | Thivyan | Dr. Sharifi
Mechanical Design | A
Robotic Arm Design | R | A | C | C | I
3D Modeling (Arm and Gripper) | R | R | I | I | I
Gripper Mechanism Design | R | C | I | I | I
FEA (Finite Element Analysis) of Arm & Gripper | R | A | I | I | I
Electrical & Programming Design |  |  | A
Selection of Electronics | I | C | R | C | I
Control System Design | C | C | R | C | I
Sensor Integration and Calibration | I | C | R | C | I
Safety Mechanisms & Emergency Protocols | I | C | R | C | I
Software Programming for Arm and UAV | I | C | R | C | I
System Testing and Troubleshooting | C | C | R | C | I
Assembly & Testing |  | A
3D Printing of Parts | C | R | I | I | I
Assembly of Robotic Arm and UAV | C | R | I | I | I
Integrated Testing and Debugging | R | A | R | R | I
Final System Calibration | R | A | R | R | I
Documentation & Reporting |  |  |  | A
Interim Report | C | C | C | R | I
Final Project Report | C | C | C | R | I
Presentation Materials | C | C | C | R | I
Field Testing Documentation | C | C | C | R | I
Final Presentation | C | C | C | R | I

## Gantt Chart V2
Aerial Manipulation Project
J2TA Engineering |  | Project Start: | 2025-01-16
|  |  |  | 2025-01-06 | [6 empty] | 2025-01-13 | [6 empty] | 2025-01-20 | [6 empty] | 2025-01-27 | [6 empty] | 2025-02-03 | [6 empty] | 2025-02-10 | [6 empty] | 2025-02-17 | [6 empty] | 2025-02-24 | [6 empty] | 2025-03-03 | [6 empty] | 2025-03-10 | [6 empty] | 2025-03-17 | [6 empty] | 2025-03-24
 | time axis 2025-01-06 to 2025-03-30
TASK | START | DAYS | END | time axis 2025-01-06 to 2025-03-30
Phase 0
LIT Review | 2025-01-16 | 29 | 2025-02-14
Project Plan | 2025-01-16 | 8 | 2025-01-24
Project Timeline | 2025-01-24 | 21 | 2025-02-14
Resposibility Assignment | 2025-01-24 | 4 | 2025-01-28
Phase 1.1 : Mechanical Design
Collect Drone and collect 3D Model | 2025-01-24 | 27 | 2025-02-20
Assembly, Testing & Calibration of Arm | 2025-02-01 | 11 | 2025-02-12
Design Base plates for Arm | 2025-02-08 | 4 | 2025-02-12
VTOL - UAV Integration | 2025-02-14 | 8 | 2025-02-22
Perform Engineering Analysis on Arm Integration | 2025-02-22 | 6 | 2025-02-28
Phase 1.2 : Manufacturing & Integration
Material Selection for Base Plate | 2025-02-09 | 3 | 2025-02-12
Refinements & Final CAD Models | 2025-02-14 | 13 | 2025-02-27
Base Plate Manufacturing | 2025-02-24 | 3 | 2025-02-27
Quadcopter UAV Integration | 2025-02-28 | 6 | 2025-03-06
Phase 2 : Electronics & Control System
Test Control Systems | 2025-02-28 | 7 | 2025-03-07
Design Electrical Circuits for Arm | 2025-02-15 | 3 | 2025-02-18
Create control system architecture | 2025-02-18 | 4 | 2025-02-22
Implement Sensors on Arm | 2025-02-22 | 5 | 2025-02-27
Implement Safety Mechanisms | 2025-02-27 | 1 | 2025-02-28
Calibrate Sensors and Fine Tune Control Algorithm | 2025-02-28 | 7 | 2025-03-07
Phase 3: Autonomous Development
Create Manual Control Interface | 2025-02-24 | 4 | 2025-02-28
Test Manual Control System | 2025-02-28 | 7 | 2025-03-07
Develop Initial Autonomous Control Algorithm | 2025-03-07 | 5 | 2025-03-12
Test Autonomous Control | 2025-03-07 | 7 | 2025-03-14
Phase 4: Final System Integration & Testing
Conduct Integrated Field Testing of UAV and Robotic Arm with semi-autonomous controls | 2025-03-07 | 7 | 2025-03-14
Phase 5: Project Report & Presentation
Engineering Report | 2025-03-14 | 6 | 2025-03-20
Conference Paper | 2025-03-20 | 5 | 2025-03-25
Presentation | 2025-03-25 | 4 | 2025-03-29
Poster | 2025-03-25 | 4 | 2025-03-29